## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Shreya | 2026-08-07 | Duplicate security event records were found during initial data validation | Sprint 1 | Shreya | Logical | Removed duplicate records and validated the cleaned dataset | 2026-08-08 | Closed | Dataset was validated before further processing
2 | Shreya | 2026-08-11 | Some security event fields contained inconsistent data types | Sprint 1 | Shreya | Logical | Standardized the data types and revalidated the dataset | 2026-08-11 | Closed | Data types were validated successfully
3 | Shreya | 2026-08-19 | Selected ML features required preprocessing before model training | Sprint 3 | Shreya | Logical | Applied categorical encoding and numerical scaling to the selected features | 2026-08-20 | Closed | Preprocessed features were validated
4 | Shreya | 2026-08-21 | Anomaly detection results required validation before further integration | Sprint 3 | Shreya | Logical | Reviewed anomaly scores and validated the Isolation Forest results | 2026-08-21 | Closed | Model output was verified
5 | Shreya | 2026-08-25 | Dashboard chart rendering caused a blank page due to a library compatibility issue | Sprint 4 | Shreya | User Interface | Replaced the problematic chart implementation with native SVG charts | 2026-08-26 | Closed | Charts displayed correctly without console errors
6 | Shreya | 2026-08-26 | Password visibility control was displaying incorrectly | Sprint 4 | Shreya | User Interface | Replaced the incorrect icon implementation with a working Show/Hide control | 2026-08-26 | Closed | Password visibility control was verified
7 | Shreya | 2026-08-27 | Prediction API response fields were not fully aligned with the required response structure | Sprint 4 | Shreya | Logical | Standardized the API response structure and verified the prediction fields | 2026-08-28 | Closed | API response was verified using Postman
8 | Shreya | 2026-09-02 | MongoDB connection was initially unavailable for incident persistence | Sprint 6 | Shreya | Logical | Verified MongoDB connectivity and configured MongoDB as the primary incident persistence layer | 2026-09-03 | Closed | Incidents were successfully persisted
9 | Shreya | 2026-09-04 | M3 API responses required additional fields to match the defined contract | Sprint 6 | Shreya | Logical | Updated the API responses with the required aliases and verified the endpoints | 2026-09-04 | Closed | Required M3 APIs returned successful responses
10 | Shreya | 2026-09-08 | Risk weight configuration displayed an incorrect percentage in the dashboard | Sprint 7 | Shreya | User Interface | Fixed the risk weight configuration display and verified the documented weights | 2026-09-08 | Closed | Risk weight display was verified
11 | Shreya | 2026-09-09 | Dashboard theme had inconsistent text and component contrast | Sprint 7 | Shreya | User Interface | Updated the theme styling and improved dark and light mode contrast | 2026-09-09 | Closed | Both themes were verified
12 | Shreya | 2026-09-10 | Dashboard-to-incident drill-down required validation | Sprint 8 | Shreya | Logical | Tested the drill-down flow from dashboard to incident and event details | 2026-09-10 | Closed | End-to-end navigation was verified
13 | Shreya | 2026-09-11 | Minor issues were identified during final end-to-end testing | Sprint 8 | Shreya | Standards | Fixed the identified issues and repeated the final validation tests | 2026-09-11 | Closed | Final system was verified before demonstration

## Sheet2
Logical
User Interface
Maintainability
Standards
Others